1. **Oxfam**

**Project Title: Flood Recovery and Response – A Community-Wide Approach**

**Partner: Oxfam**

* **Project Duration:** September 2022 – July 2024
* **Budget:** **PKR 1455 Million**
* **Regions Covered:** Sindh & Balochistan
* **Districts:**
  + **Sindh:** Mirpurkhas, Sanghar
  + **Balochistan:** Jaffarabad, Sohbatpur
* **Primary Beneficiaries:**
  + Vulnerable flood-affected communities
  + Women, children, and persons with disabilities (PWDs)

**Project Overview**

This initiative aimed to provide safe and affordable drinking water, sanitation, and hygiene services to flood-affected communities in Sindh and Balochistan. With a strong focus on women, children, and PWDs, the project also addressed food security, economic recovery, and disaster preparedness to build resilience against future climate-induced disasters.

**Key Initiatives & Achievements**

**Community Engagement & Governance**

* **20 Village Committees** established to ensure local representation in decision-making.
* **Real-Time Review (RTR)** conducted to assess progress and challenges in affected areas.

**Water, Sanitation, and Hygiene (WASH) Interventions**

* **112 bore handpumps** installed, benefiting 784 individuals.
* **700 water filters (Nadi/Bio Sand)** distributed, providing clean water to 4,900 people.
* **48 latrines** constructed, improving sanitation for 4,312 people.
* **29 bathing spaces** built to enhance hygiene and dignity.
* **370 handwashing stations** set up, benefiting 25,900 individuals.
* **22 village cleaning campaigns** conducted to promote hygiene and disease prevention.
* **Solar-powered filtration plants and bio-sand filters** installed, supplying clean drinking water to over 80 households.

**Non-Food Items (NFI) Distribution**

* **9,000 NFI kits** distributed to vulnerable households.
* **4,000 winter kits** provided to protect against harsh weather conditions.

**Food and Economic Security (FES) Support**

* **134 individuals (64 women, 92 men)** supported with agricultural inputs (seeds, fertilizers, farming tools).
* **17 women-led kitchens** established, promoting food security and economic empowerment.
* **5,117 livestock animals** vaccinated and dewormed to ensure sustainable livelihoods.

**Protection & Community Resilience**

* **55 Community-Based Protection (CBP) Committees** formed, engaging **543 women and 40 men** in safety and disaster preparedness.
* **Disaster Preparedness Training** conducted in collaboration with District Disaster Management Authority (DDMA), training **34 participants (5 women, 29 men)** in emergency response strategies.

**Impact & Sustainability**

* Strengthened **community resilience** through disaster preparedness and governance structures.
* Improved **health and hygiene** through increased access to safe drinking water and sanitation.
* Enhanced **food security and economic recovery** by supporting agriculture, livestock care, and women-led businesses.
* Created **inclusive, gender-responsive, and disaster-resilient communities** in Sindh and Balochistan.

This project served as a **lifeline for flood-affected communities**, ensuring both **immediate relief** and **long-term recovery** while building resilience against future climate-related disasters.